## Sheet1
Online Movie Ticket Booking System
Company- LTTS
Lead by- Akruti Jain
Task | Start Date | Days to complete
Requirement specification and Analysis | 2022-03-17 | 1
Design | 2022-03-18 | 1
Test Cases | 2022-03-19 | 2
Coding with unit testing | 2022-03-21 | 4
Testing | 2022-03-25 | 4
Documentation | 2022-03-29 | 1